## Sheet1
Task | Task | IT Consultant | Programming Expert | Interface Design Expert | Database Administrator | Quality Assurance Tester
1 | Link user queries to downloadable delivery history | C | A | I | R | I | C= Consulted
2 | Integrate related API's for the app to retrieve tracking information | C | R | I | I | I | I= Informed
3 | Store and retrieve user account information | C | A | I | R | I | R=Responsible
4 | Create and present interface for user to navigate | C | A | R | I | I | A=Accountable
5 | Ensure feature parity between commonly used target devices | C | A | A | A | R
6 | Ensure team understands next steps | R | A | I | I | I
7 | Ensure team understands project scope and stakeholder expectations | R | C | I | I | I
8 | Communicate with project lead (Programming Expert) to navigate risks and issues | R | A | C | C | I
9 | Highlight areas of improvements, and bugs in design | I | A | A | I | R
10 | Scale programming implementations based on available time resources | A | R | C | C | C
11 | Generate milestones for team to follow | R | A | I | I | I
12 | Document codebase for organization and user troubleshooting | I | C | C | C | R